## Original System
Component | Type | Quantity | Unit Cost £ | Manufacturing Cost £ | Total
CPU | 68K8 | 1 | 15 | 0 | 15
Board | A83-S | 1 | 25 | 14 | 39
ULA | G1 | 1 | 5 | 4 | 9
| G2 | 1 | 5 | 4 | 9
| G3 | 1 | 5 | 4 | 9
| G4 | 1 | 5 | 4 | 9
ROM | 32K | 2 | 30 | 0 | 30
RAM | 32Kb | 4 | 5 | 0 | 5
INTSND | i8042 | 1 | 1.5 | 0 | 1.5
STORAGE | cartridge | 2 | 5 | 0 | 5
IOP-J | SC100 | 1 | 9 | 2 | 11
| SC150 | 1 | 9 | 2 | 11
CASE | DESKTOP | 1 | 25 | 5 | 30
Misc | resistors, caps, etc | 100 | 0.05 | 0 | 0.05
EZ-SYS | EZ-Suite |  |  |  | 25
Total |  |  | 144.55 | 39 | 208.55
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Hardware Architect (IN-HOUSE) | 250 | 60 | CPU | 68K8 | 0 | 0 | 0 | 2 | 5 | 1250
|  |  | Board | A83-S | 8 | 25 | 6250 | 0 | 0 | 0
|  |  | ROM | 32K | 8 | 15 | 3750 | 2 | 5 | 1250
|  |  | RAM | 32Kb | 0 | 0 | 0 | 2 | 5 | 1250
|  |  | IOP-J | SC100 | 2 | 5 | 1250 | 1 | 2.5 | 625
|  |  | IOP-J | SC150 | 2 | 5 | 1250 | 1 | 2.5 | 625
|  |  | INTSND | i8042 | 0 | 0 | 0 | 1 | 2.5 | 625
|  |  | CASE | DESKTOP | 10 | 10 | 2500 | 5 | 10 | 2500
Hardware Architect (Agency) | 400 | 60 | ULA | G1 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G2 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G3 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G4 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | STORAGE | cartridge | 0 | 0 | 0 | 2 | 5 | 2000
|  |  | CASE | DESKTOP | 10 | 20 | 8000 | 5 | 0 | 0
|  |  | Misc | resistors, caps, etc | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 64 | 120 | 39000 | 29 | 57.5 | 18125
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Hardware Engineer (IN-HOUSE) | 175 | 185 | CPU | 68K8 | 0 | 0 | 0 | 2 | 5 | 875
|  |  | Board | A83-S | 8 | 30 | 10500 | 0 | 0 | 0
|  |  | ROM | 32K | 8 | 25 | 8750 | 2 | 5 | 875
|  |  | RAM | 32Kb | 0 | 0 | 0 | 2 | 5 | 875
|  |  | IOP-J | SC100 | 2 | 5 | 1750 | 1 | 2.5 | 437.5
|  |  | IOP-J | SC150 | 2 | 5 | 1750 | 1 | 2.5 | 437.5
|  |  | INTSND | i8042 | 0 | 0 | 0 | 1 | 2.5 | 437.5
|  |  | CASE | DESKTOP | 10 | 40 | 14000 | 5 | 10 | 1750
|  |  | ULA | G1 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G2 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G3 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G4 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | STORAGE | cartridge | 0 | 0 | 0 | 2 | 5 | 875
|  |  | Misc | resistors, caps, etc | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 54 | 185 | 64750 | 24 | 57.5 | 10062.5
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Software Architect (IN-HOUSE) | 300 | 60 | Operating System | Boot ldr & HWcfg | 2 | 5 | 1500 | 2 | 5 | 1500
|  |  |  | Sys: Kernel | 8 | 15 | 4500 | 6 | 10 | 3000
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 2550
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 750
|  |  |  | SYS: Extensions | 2 | 2.5 | 750 | 3 | 6.5 | 1950
|  |  |  | SYS: GameSnd | 2 | 2.5 | 750 | 2 | 5 | 1500
|  |  |  | SYS: Graphics | 4 | 10 | 3000 | 2 | 5 | 1500
|  |  |  | BAS: Kernel | 8 | 12.5 | 3750 | 4 | 8.5 | 2550
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 2550
|  |  |  | BAS: fs libs | 2 | 2.5 | 750 | 2 | 5 | 1500
|  |  |  | EZ-Suite | 10 | 10 | 3000 | 8 | 10 | 3000
Software Architect (Agency) | 450 | 60 | Operating System | Boot ldr & HWcfg | 2 | 5 | 2250 | 2 | 5 | 2250
|  |  |  | Sys: Kernel | 8 | 15 | 6750 | 6 | 10 | 4500
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 3825
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 1125
|  |  |  | SYS: Extensions | 2 | 2.5 | 1125 | 3 | 6.5 | 2925
|  |  |  | SYS: GameSnd | 2 | 2.5 | 1125 | 2 | 5 | 2250
|  |  |  | SYS: Graphics | 4 | 10 | 4500 | 2 | 5 | 2250
|  |  |  | BAS: Kernel | 8 | 12.5 | 5625 | 4 | 8.5 | 3825
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 3825
|  |  |  | BAS: fs libs | 2 | 2.5 | 1125 | 2 | 5 | 2250
|  |  |  | EZ-Suite | 10 | 10 | 4500 | 8 | 10 | 4500
Total |  |  |  |  | 76 | 120 | 45000 | 78 | 149 | 55875
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Software Engineer (IN-HOUSE) | 195 | 185 | Operating System | Boot ldr & HWcfg | 2 | 10 | 3900 | 2 | 5 | 1950
|  |  |  | Sys: Kernel | 8 | 40 | 15600 | 6 | 10 | 3900
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 3315
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 975
|  |  |  | SYS: Extensions | 2 | 10 | 3900 | 3 | 6.5 | 2535
|  |  |  | SYS: GameSnd | 2 | 10 | 3900 | 2 | 5 | 1950
|  |  |  | SYS: Graphics | 4 | 20 | 7800 | 2 | 5 | 1950
|  |  |  | BAS: Kernel | 8 | 40 | 15600 | 4 | 8.5 | 3315
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 3315
|  |  |  | BAS: fs libs | 2 | 10 | 3900 | 2 | 5 | 1950
|  |  |  | EZ-Suite | 10 | 45 | 17550 | 8 | 10 | 3900
Total |  |  |  |  | 38 | 185 | 72150 | 39 | 74.5 | 29055
Total Hardware Labour | 103750
Total Software Labour | 117150
Total | 229150
Material Cost £ | 260.55
Systems ordered | 2000
Total Cost £ | 521100
Total Overall Cost £ | 750250
Budgeted Amount £ | 500000
Profit/Loss | -250250

## Upgraded System
Component | Type | Quantity | Unit Cost £ | Manufacturing Cost £ | Total
CPU | 68K0 | 1 | 25 | 0 | 25
Board | A83-S | 1 | 25 | 14 | 39
ULA | G1 | 1 | 5 | 4 | 9
| G2 | 1 | 5 | 4 | 9
| G3 | 1 | 5 | 4 | 9
| G4 | 1 | 5 | 4 | 9
ROM | 32K | 2 | 30 | 0 | 30
RAM | 512Kb | 4 | 25 | 0 | 25
INTSND | i8042 | 1 | 1.5 | 0 | 1.5
STORAGE | cartridge | 2 | 5 | 0 | 5
IOP-J | SC100 | 2 | 9 | 2 | 22
| SC150 | 2 | 9 | 2 | 22
CASE | DESKTOP | 1 | 25 | 5 | 30
Misc | resistors, caps, etc | 100 | 0.05 | 0 | 0.05
EZ-SYS | EZ-Suite |  |  |  | 25
Total |  |  | 174.55 | 39 | 260.55
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Hardware Architect (IN-HOUSE) | 250 | 60 | CPU | 68K0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Board | A83-S | 8 | 25 | 6250 | 0 | 0 | 0
|  |  | ROM | 32K | 8 | 15 | 3750 | 2 | 5 | 1250
|  |  | RAM | 512Kb | 0 | 0 | 0 | 2 | 5 | 1250
|  |  | IOP-J | SC100 | 2 | 5 | 1250 | 1 | 2.5 | 625
|  |  | IOP-J | SC150 | 2 | 5 | 1250 | 1 | 2.5 | 625
|  |  | INTSND | i8042 | 0 | 0 | 0 | 1 | 2.5 | 625
|  |  | CASE | DESKTOP | 10 | 10 | 2500 | 5 | 10 | 2500
Hardware Architect (Agency) | 400 | 60 | ULA | G1 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G2 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G3 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | ULA | G4 | 6 | 10 | 4000 | 2 | 5 | 2000
|  |  | STORAGE | cartridge | 0 | 0 | 0 | 2 | 5 | 2000
|  |  | CASE | DESKTOP | 10 | 20 | 8000 | 5 | 0 | 0
|  |  | Misc | resistors, caps, etc | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 64 | 120 | 39000 | 27 | 52.5 | 16875
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Hardware Engineer (IN-HOUSE) | 175 | 185 | CPU | 68K8 | 0 | 0 | 0 | 2 | 5 | 875
|  |  | Board | A83-S | 8 | 30 | 10500 | 0 | 0 | 0
|  |  | ROM | 32K | 8 | 25 | 8750 | 2 | 5 | 875
|  |  | RAM | 32Kb | 0 | 0 | 0 | 2 | 5 | 875
|  |  | IOP-J | SC100 | 2 | 5 | 1750 | 1 | 2.5 | 437.5
|  |  | IOP-J | SC150 | 2 | 5 | 1750 | 1 | 2.5 | 437.5
|  |  | INTSND | i8042 | 0 | 0 | 0 | 1 | 2.5 | 437.5
|  |  | CASE | DESKTOP | 10 | 40 | 14000 | 5 | 10 | 1750
|  |  | ULA | G1 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G2 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G3 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | ULA | G4 | 6 | 20 | 7000 | 2 | 5 | 875
|  |  | STORAGE | cartridge | 0 | 0 | 0 | 2 | 5 | 875
|  |  | Misc | resistors, caps, etc | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 54 | 185 | 64750 | 24 | 57.5 | 10062.5
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Software Architect (IN-HOUSE) | 300 | 60 | Operating System | Boot ldr & HWcfg | 2 | 2.5 | 750 | 2 | 5 | 1500
|  |  |  | Sys: Kernel | 8 | 10 | 3000 | 6 | 10 | 3000
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 2550
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 750
|  |  |  | SYS: Extensions | 2 | 2.5 | 750 | 3 | 6.5 | 1950
|  |  |  | SYS: GameSnd | 2 | 2.5 | 750 | 2 | 5 | 1500
|  |  |  | SYS: Graphics | 4 | 5.5 | 1650 | 2 | 5 | 1500
|  |  |  | BAS: Kernel | 8 | 5.5 | 1650 | 4 | 8.5 | 2550
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 2550
|  |  |  | BAS: fs libs | 2 | 2.5 | 750 | 2 | 5 | 1500
|  |  |  | BAS: GUI | 8 | 10 | 3000 | 4 | 8.5 | 2550
|  |  |  | Emulator | 6 | 5.5 | 1650 | 2 | 2.5 | 750
|  |  |  | EZ-Suite | 10 | 6 | 1800 | 8 | 10 | 3000
Software Architect (Agency) | 450 | 60 | Operating System | Boot ldr & HWcfg | 2 | 2.5 | 1125 | 2 | 5 | 2250
|  |  |  | Sys: Kernel | 8 | 15 | 6750 | 6 | 10 | 4500
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 3825
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 1125
|  |  |  | SYS: Extensions | 2 | 2.5 | 1125 | 3 | 6.5 | 2925
|  |  |  | SYS: GameSnd | 2 | 2.5 | 1125 | 2 | 5 | 2250
|  |  |  | SYS: Graphics | 4 | 10 | 4500 | 2 | 5 | 2250
|  |  |  | BAS: Kernel | 8 | 10 | 4500 | 4 | 8.5 | 3825
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 3825
|  |  |  | BAS: fs libs | 2 | 2.5 | 1125 | 2 | 5 | 2250
|  |  |  | BAS: GUI | 8 | 10 | 1950 | 4 | 8.5 | 3825
|  |  |  | Emulator | 6 | 5.5 | 1072.5 | 2 | 2.5 | 1125
|  |  |  | EZ-Suite | 10 | 7 | 3150 | 8 | 10 | 4500
Total |  |  |  |  | 104 | 120 | 42172.5 | 90 | 171 | 64125
Role | Labour Cost £ (per day) | Total Days | Component | Type | Design Weeks | Days Allocated to role | Design Cost £ | Redesign Weeks | Day Allocated to Role | Redesign Cost £
Software Engineer (IN-HOUSE) | 195 | 185 | Operating System | Boot ldr & HWcfg | 2 | 5 | 1950 | 2 | 5 | 1950
|  |  |  | Sys: Kernel | 8 | 30 | 11700 | 6 | 10 | 3900
|  |  |  | SYS: Libraries | 0 | 0 | 0 | 4 | 8.5 | 3315
|  |  |  | SYS: Drivers | 0 | 0 | 0 | 2 | 2.5 | 975
|  |  |  | SYS: Extensions | 2 | 5.5 | 2145 | 3 | 6.5 | 2535
|  |  |  | SYS: GameSnd | 2 | 5.5 | 2145 | 2 | 5 | 1950
|  |  |  | SYS: Graphics | 4 | 15 | 5850 | 2 | 5 | 1950
|  |  |  | BAS: Kernel | 8 | 35 | 13650 | 4 | 8.5 | 3315
|  |  |  | BAS: core lib&I/O | 0 | 0 | 0 | 4 | 8.5 | 3315
|  |  |  | BAS: fs libs | 2 | 5.5 | 2145 | 2 | 5 | 1950
|  |  |  | BAS: GUI | 8 | 30 | 11700 | 4 | 8.5 | 3315
|  |  |  | Emulator | 6 | 20 | 7800 | 2 | 2.5 | 975
|  |  |  | EZ-Suite | 10 | 33.5 | 13065 | 8 | 10 | 3900
Total |  |  |  |  | 52 | 185 | 72150 | 45 | 85.5 | 33345
Total Hardware Labour | 103750 |  | Total Redesign | 366.5
Total Software Labour | 0
Total

## Sheet4
Cost of Materials £ | 208.55
Pre-Ordered | 3000
Labor £ | 229150
Total Cost £ | 854800
Selling Price £ | 399
Total Revenue | 1197000
Profit/Loss | 342200

## Sheet5
Milestones
Synputer 1: This was the Original prototyped model with condierations to the requirements that were set forth
Project Report: This was sent to EDC and criticsms were highlighted
Synputer 2.0: We went back to the drawingf board.
EDC Requirements Fulfilled: The Team made every effort to meet the requirments set forth by EDC
Consumer and Beyond: We will now market both models to consumers