## Slide 1: SyNFUL Computing
Project Update
February 2024
University of ESSEX
Presenter: JORDEL DAVIDSON-SWANN

## Slide 2: introduction
Thank you for taking the time to join me for this Project Update Presentation.
This update is meant to inform on what has been going on in the current Project inflight of the feedback that was received from EDC

## Slide 3: Agenda
Project Milestones
Original Budget
Previous Specifications
Requirements Table
Costed Project Plan
Timeline
Going Forward

## Slide 4: Project Milestones
Milestones
Synputer 1: This was the Original prototyped model with condierations to the requirements that were set forth
Project Report: This was sent to EDC and criticsms were highlighted
Synputer 2.0: We went back to the drawingf board.
EDC Requirements Fulfilled: The Team made every effort to meet the requirments set forth by EDC
Consumer and Beyond: We will now market both models to consumers

## Slide 5: Original Budget
Role | # of Employee | Cost/Day | Total Days | Total Cost
Project Manager | 1 | £275.00 | 30 | £8,250.00
Hardware Architect (Inhouse) | 1 | £250.00 | 60 | £15,000.00
Hardware Architect (Agency) | 1 | £400.00 | 60 | £24,000.00
HW Engineer (inhouse) | 2 | £175.00 | 185 | £64,750.00
Software Architect | 1 | £300.00 | 60 | £18,000.00
SW Engineer |  | £195.00 | 185 | £72,150.00
Software Architect (Agency) | Payment Received | £450.00 | 60 | £27,000.00
TOTAL |  |  |  | £229,150.00
 |  | Amount £ | Amount £
Payment Received |  |  | 500,000.00
Expenses: | Labour | 229,150.00 | 
 | Materials | 220,850.00 | 
 | Overhead | 50,000.00 | 
 | Total Expenses | 500,000.00 | (500,000.00)
 |  |  | 0.00

## Slide 6: Original System Specifications
Component | Type | Quantity | Unit Cost £ | Manufacturing Cost £ | Total
CPU | 68K8 | 1 | 15 | 0 | 15
Board | A83-S | 1 | 25 | 14 | 39
ULA | G1 | 1 | 5 | 4 | 9
 | G2 | 1 | 5 | 4 | 9
 | G3 | 1 | 5 | 4 | 9
 | G4 | 1 | 5 | 4 | 9
ROM | 32K | 2 | 30 | 0 | 30
RAM | 32Kb | 4 | 5 | 0 | 5
INTSND | i8042 | 1 | 1.5 | 0 | 1.5
STORAGE | cartridge | 2 | 5 | 0 | 5
IOP-J | SC100 | 1 | 9 | 2 | 11
 | SC150 | 1 | 9 | 2 | 11
CASE | DESKTOP | 1 | 25 | 5 | 30
Misc | resistors, caps, etc | 100 | 0.05 | 0 | 0.05
EZ-SYS | EZ-Suite |  |  |  | 25
Total |  |  | 144.55 | 39 | 208.55

## Slide 7: Table OF REQUIREMENTS
REQUIREMENT | WAS IT MET? | JUSTIFICATION
Industry Standard OS | YES. The HyperBasic/OS definitely meets the standard of industry | HyperBasic is the OS designed by our team and is what is most appropritate especially when one looks at the specifications of the other Operating Systems
External Keyboard/Connector | YES.Comes with two(2) IOP-J SC150 2ch that supports keyboard,mouse and joystick | Having 2 IOP-J will allow for dual use of keyboard,mouse and joystick or a combination.
At least 512KB of RAM | YES. System now allows for 4 512KB of Ram for a maximum RAM of 2MB | Having an abundance of RAM will assist in multitasking in HB/OS GUI, accelerating productivity and usability of the system
Removable Media Drive | YES. System supports 2 removable cartridge drives | Two cartridges will allow for easy emulation and storage control
SCSI Expansion Capability | No | When evaluating everything the system required, this expansion slot was found to be inadequate. It does not provide the 4 slots for ULA.
68000 CPU or Upgradable | YES. The CPU is a 68k series that offers 8MHz, 16/32, 16MB max RAM | This is a CPU that is better than many others and because of the choice to use a socketed board, if users are not satisfied then they can simply swap this for an upgraded CPU.
2 Serial Ports (RS422/RS485) | YES. The system comes with two (2) IOP-J SC100 2ch MPX serial ports | Users may require serial ports for connecting to legacy hardware or industrial equipment using RS422/RS485 protocols.
GUI Support | YES. The system has been outfitted to do so with connection ports and software included. | This was a requirement that was asked to be inplemented and it was seen by our team that the potential market to outside users would also want this

## Slide 8: Cost Project Plan
Component | Type | Quantity | Unit Cost £ | Manufacturing Cost £ | Total
CPU | 68K8 | 1 | 15 | 0 | 15
Board | A83-S | 1 | 25 | 14 | 39
ULA | G1 | 1 | 5 | 4 | 9
 | G2 | 1 | 5 | 4 | 9
 | G3 | 1 | 5 | 4 | 9
 | G4 | 1 | 5 | 4 | 9
ROM | 32K | 2 | 30 | 0 | 30
RAM | 32Kb | 4 | 5 | 0 | 5
INTSND | i8042 | 1 | 1.5 | 0 | 1.5
STORAGE | cartridge | 2 | 5 | 0 | 5
IOP-J | SC100 | 1 | 9 | 2 | 11
 | SC150 | 1 | 9 | 2 | 11
CASE | DESKTOP | 1 | 25 | 5 | 30
Misc | resistors, caps, etc | 100 | 0.05 | 0 | 0.05
EZ-SYS | EZ-Suite |  |  |  | 25
Total |  |  | 144.55 | 39 | 208.55

## Slide 9: Cont’d
Total Hardware Labour | 103750
Total Software Labour | 117150
Total | 229150
Material Cost £ | 208.55
Systems ordered | 2000
Total Cost £ | 417100
Total Overall Cost £ | 646250
Budgeted Amount £ | 500000
Profit/Loss | -146250

## Slide 10: Cont’d
Component | Type | Quantity | Unit Cost £ | Manufacturing Cost £ | Total
CPU | 68K0 | 1 | 25 | 0 | 25
Board | A83-S | 1 | 25 | 14 | 39
ULA | G1 | 1 | 5 | 4 | 9
 | G2 | 1 | 5 | 4 | 9
 | G3 | 1 | 5 | 4 | 9
 | G4 | 1 | 5 | 4 | 9
ROM | 32K | 2 | 30 | 0 | 30
RAM | 512Kb | 4 | 25 | 0 | 25
INTSND | i8042 | 1 | 1.5 | 0 | 1.5
STORAGE | cartridge | 2 | 5 | 0 | 5
IOP-J | SC100 | 2 | 9 | 2 | 22
 | SC150 | 2 | 9 | 2 | 22
CASE | DESKTOP | 1 | 25 | 5 | 30
Misc | resistors, caps, etc | 100 | 0.05 | 0 | 0.05
EZ-SYS | EZ-Suite |  |  |  | 25
Total |  |  | 174.55 | 39 | 260.55

## Slide 11: Cont’d
Total Hardware Labour | 103750
Total Software Labour | 117150
Total | 229150
Material Cost £ | 260.55
Systems ordered | 2000
Total Cost £ | 521100
Total Overall Cost £ | 750250
Budgeted Amount £ | 500000
Profit/Loss | -250250

## Slide 12: TimeLine
  Expert Judgement 46 weeks
  Program Evaluation and Review Technique (PERT)
  Optimistic Time – 46 weeks
  Most Likely Time – 56 weeks
  Pessimistic Time – 75 weeks
  Expected Time – 57 Weeks

## Slide 13: Going Forward
Cost of Materials £ | 208.55
Pre-Ordered | 3000
Labor £ | 229150
Total Cost £ | 854800
Selling Price £ | 399
Total Revenue | 1197000
Profit/Loss | 342200

## Slide 14: Premium Model
Sell the machine requersted by EDC to consumers for £599.00

## Slide 15: Thank You